WOAH/AUIBAR/TADs/OCT/2026

# Simplified Consultation of Suppliers

# A.Tender Procedure rules

# OPEN CALL FOR EXPERTS

# Scoping and Feasibility Study for the Establishment of a Continental Emergency Fund for Transboundary Animal Diseases in Africa

# WORLD ORGANISATION FOR ANIMAL HEALTH (WOAH) 
whose statutory name is 
“OFFICE INTERNATIONAL DES EPIZOOTIES”

# deadline to submit offers: 6th November 2026

| Contracting authority |  |
| --- | --- |
| World Organisation for Animal Health (WOAH) whose statutory name is “Office international des epizooties” 12 Rue de Prony F-75017 Paris France |  |

TABLE OF CONTENTS

1.	FRAMEWORK OF THE TENDER PROCEDURE	4

1.1.	Contracting authority	4

1.2.	Definitions	5

1.3.	Choice of procurement procedure	5

1.4.	Purpose	5

1.5.	Project Background	5

1.6.	Project objectives	6

1.7.	Duration of the contract-Renewal-Timeframes	6

1.7.1.	Duration and renewal	6

1.7.2.	Timeframes	6

1.8.	Financial Estimate	6

1.9.	Typology of procurements and prices	6

2.	GENERAL TENDER RULES	7

2.1.	Condition of participation	7

2.1.1.	Cocontracting	7

2.1.2.	Subcontracting	7

2.2.	Requirement to access	7

2.3.	Conflicts of Interest	8

2.4.	Confidentiality	8

2.5.	Costs of Responses	9

2.6.	Non-binding Effect	9

2.7.	WOAH’s right	9

2.7.1.	Modification	9

2.7.2.	Cancellation of the simplified consultation of suppliers	9

2.8.	Appeal	10

3.	TENDER PROCESS DETAILS	10

3.1.	Procedure	10

3.2.	Tender dossier	10

3.2.1.	Questions	10

3.3.	Content of tenders and its selection	11

3.4.	Proposal structure	11

3.4.1.	Information and Administrative documents	12

3.4.2.	Technical response	12

3.4.3.	Financial response	12

3.4.4.	Evaluation of tenders	13

3.5.	Regularisation of tenders	13

3.6.	Period of Proposal Validity	13

3.7.	Personal data	13

3.8.	Publication of information on recipients	14

3.9.	Awarding contract	14

Annexes	14

# FRAMEWORK OF THE TENDER PROCEDURE

## Contracting authority

World Organisation for Animal Health (WOAH) whose statutory name is 
 “Office International des Epizooties”.

12 Rue de Prony

75017 Paris

France

Tél. : 33 – (0)1 44 15 18 88

Fax : 33 – (0)1 42 67 09 87

Website : Home - WOAH - World Organisation for Animal Health

WOAH was founded on 25 January 1924.

WOAH is an intergovernmental organisation governed by international public law.

Its mission is to improve animal health worldwide. The standards it draws up for trade in live animals and animal products are recognised by the World Trade Organisation (WTO) as international health rules of reference.

WOAH 's mission is to:

Ensure transparency of the animal disease situation worldwide;

Collect, analyse and disseminate scientific veterinary information;

Provide expertise and stimulate international solidarity to control animal diseases;

To guarantee the safety of world trade by drawing up health standards for international trade in animals and animal products within the framework of the mandate given to WOAH by the WTO SPS Agreement;

Promote the legal framework and resources of veterinary services;

Better guarantee food safety and promote animal welfare using a scientific approach.

As established by the International Treaty of 25 January 1924 creating the Organisation, its headquarters are located in Paris.

It has 183 Members and is present on every continent through a total of 13 Representations or Offices.

The Organisation employs more than 250 staff, divided between the headquarters (60% of the workforce) and its 13 Representations on 5 continents.

WOAH maintains permanent contact with 71 other international organisations and 301 Reference Centres and Laboratories in its 3 official languages, French, English and Spanish, through the staff at its Paris headquarters and its 13 Regional and Sub-Regional Representations on every continent.

The signatory of the contract will be  WOAH Director General.

WOAH Point of contact

Dr Neo Mapitse WOAH Sub-regional Representation for eastern Africa E-mail n.mapitse@woah.org

## Definitions

Awarded Tenderer: the economic operator having, through the simplified consultation of suppliers process, been awarded the contract, prior to its signature.

Contract: the definitive agreement for Services entered into by WOAH and the Supplier, including any annexes attached thereto, as amended, modified and supplemented from time to time.

Supplier: the economic operator having signed the contract with WOAH for the provision of the services detailed in this simplified consultation of suppliers, together with all its subcontractors. This operator will be the sole interlocutor of WOAH.

Services: the services, functions, responsibilities, tasks and deliverables to be carried out by the Supplier, as described in the Contract.

Tenderers: all economic operators responding to this tender procedure.

## Choice of procurement procedure

For simplified consultations of suppliers with an estimated value of less than € 30 000 excluding VAT, WOAH may use a simplified consultation of suppliers.

## Purpose

This simplified consultation of suppliers (“tender procedure”) is an invitation for interested service providers to submit a proposal to determine whether, and under what institutional, legal, financial and operational conditions, a standing Africa TADs Emergency Fund can be established as a credible, rapidly deployable and sustainable financing facility under the GF-TADs Africa framework.

## Project Background

Africa’s livestock sector supports an estimated 800 million people and contributes substantially to agricultural GDP, food security, employment and trade. Yet recurrent transboundary animal disease (TAD) emergencies can abruptly disrupt regional value chains, close export markets, erode livelihoods and reverse public and private investment. Current response financing is often mobilised after an outbreak has already spread, through country-specific and time-consuming programme or donor processes.

AU-IBAR, as current Chair of the GF-TADs Regional Steering Committee for Africa, has proposed an Africa TADs Emergency Fund: a standing, ring-fenced and replenishable financing facility capable of releasing resources rapidly following a verified emergency. The proposed Fund would complement existing human-health and humanitarian financing mechanisms by addressing the animal-health source of zoonotic threats as well as economically damaging non-zoonotic diseases such as foot-and-mouth disease, peste des petits ruminants, African swine fever, contagious bovine pleuropneumonia and lumpy skin disease.

The concept is also intended to support AU-IBAR’s Integrated Regional Livestock Value Chains (IRLVC) programme by reducing catastrophic animal-health risk in livestock corridors, protecting safe trade and helping crowd in public, development-finance and private investment. Initial geographic consideration covers COMESA, IGAD, ECOWAS and EAC, with scope for later continental expansion

## Project objectives

This simplified consultation of suppliers is an invitation to potential service providers to submit a tender in accordance with undertaking an integrated scoping and feasibility study and develop a practical, evidence-based pathway for establishing the proposed Fund. The study must move beyond a general concept: it should test demand, examine viable options, recommend a preferred model, and present a donor- and investor-ready business case and implementation roadmap.

Specifically;

Assess the scale, nature and consequences of the emergency-financing gap for priority TADs in Africa.

Map and benchmark relevant emergency, contingency, pooled, revolving, insurance, guarantee and blended-finance mechanisms in Africa and globally.

Assess stakeholder demand, political economy, institutional readiness and the incentives of Member States, RECs, development partners, DFIs, insurers and private-sector actors.

Evaluate legal, governance, fiduciary, operational and financial options for establishing and hosting the Fund.

Estimate realistic capital requirements, financing sources, replenishment arrangements and sustainability scenarios.

Recommend a feasible operating model, including activation triggers, decision rights, disbursement channels, safeguards and accountability arrangements.

Develop a phased establishment roadmap and a compelling business case for resource mobilisation.

## Duration of the contract-Renewal-Timeframes

### Duration and renewal

The Contract is expected to be performed from November 2026 for a duration of 3 months.

The contract will not be renewed

### Timeframes

The timeframe will be studied according to the solutions proposed during the negotiation with the selected Tenderers and specified by WOAH before the submission of the final offer. The actual schedule will depend on the real date of the contract signing and the time assessment of the chosen Service Provider. A general time frame is provided below;

| No. | Deliverable | Days | Indicative timing |
| --- | --- | --- | --- |
| 1 | Inception report: refined questions, methodology, feasibility framework, stakeholder map, workplan and consultation tools. | 5 | Within 7 calendar days of contract start |
| 2 | Scoping and benchmarking report: financing-gap analysis, stakeholder-demand findings, case studies and longlist of institutional/financing options. | 12 | By end of Week 4 |
| 3 | Options and feasibility report: comparative assessment of at least three options; preliminary legal, fiduciary, operational and financial model; capitalisation scenarios and risk analysis. | 14 | By end of Week 7 |
| 4 | Stakeholder validation workshop and concise presentation of findings, preferred option and outstanding decisions. | 3 | Week 8 |
| 5 | Final feasibility study and business case: recommended model, theory of change/results framework, governance and operating architecture, financing and resource-mobilisation strategy, implementation roadmap, draft term sheet/outline Fund Charter and executive summary. | 11 | Within 12 weeks of contract start |

## Financial Estimate

WOAH has decided not to indicate the budget.

Tenderers are invited to submit the most favourable and adapted financial offer; this financial offer will be part of the assessment (see Section 4.1.4.).

## Typology of procurements and prices

The contract will be concluded on the basis of prices expressed in euros (€).

# GENERAL TENDER RULES

## Condition of participation

Natural and legal persons as well as consortia (either officially established or constituted specifically for this simplified consultation of suppliers) may apply.

No more than one tender may be submitted by a person whether as a natural or legal person or member of a consortium. If a person submits more than one response, all responses in which they participate will be excluded from the selection process.

### Cocontracting

Tenderer responding with one or more co-contractors (consortium), must indicate in the Declaration of co-contractors (Annex B2) :

whether it is joint-and-several liability or joint-liability only,

the member who represents the consortium by providing a power of attorney.

Each co-contractor shall provide all administrative information and documents requested (Document B-Administrative Information)

Each co-contractor must be validated by WOAH (see 2.2).

WOAH reserves the right to impose to the selected tenderer applying as part of a consortium with joint liability only to switch its constitution to the joint and several liability between the members of the consortium.

### Subcontracting

Subcontracting is allowed; in that case, it must not exceed 49% (on the basis of workload or price evaluation) and declaration of subcontractors shall be made by using the document provided in Appendix B3.

Each subcontractor must be validated for integrity by WOAH (see 2.2). The intention to participate and to subcontract must be precisely identified according to the proposed phases of the project as well as the rate of subcontracting.

## Requirement to access

In participating to this simplified consultation of suppliers, a tenderer represents and warrants by doing so that:

is not bankrupt or under mandatory liquidation, is not having its affairs administered by the courts, has not entered into an arrangement with creditors, is not the subject of proceedings concerning its business activities, or is not in any similar situation arising from a procedure provided for in national legislation or regulations;

it or a person having powers of representation, decision-making or control over it or a member of an administrative, a management or a supervisory body has not been the subject of a judgment which has the force of res judicata for fraud, corruption, involvement in a criminal organization, money laundering, offences linked to terrorist activities, child labour, human trafficking, creating or being a shell company or any other irregular or illegal activity;

it or persons having powers of representation, decision-making or control over it have not been guilty of professional misconduct, including misrepresentation.

it is in compliance with all its obligations relating to the payment of social security contributions and of taxes in accordance with the national legislation or regulations of the country in which the Tenderer is established.

Tenderers undertake to provide documentary evidence related to the items mentioned above upon request by WOAH at any point during the tender procedure and/or contracting process. Should a tenderer fail to produce reasonable evidence, WOAH reserves the right to reject the tenderer’s response and, in the event it has already entered into a Contract with the tenderer as a result of the tender process, to terminate such Contract with immediate effect.

The REFINITIV WORLD-CHEK ONE global compliance screening platform will be consulted. 
In accordance with WOAH’s internal rules, the identification of a tenderer by this platform may lead to its exclusion.

## Conflicts of Interest

Under no circumstances is a tenderer to contact any person employed by or representing WOAH. regarding the tender procedure other than the person(s) mentioned in this document.

In participating to this simplified consultation of suppliers, a tenderer represents and warrants that:

It does not have any conflict of interest arising from economic interests, political or national affinities, family or emotional ties, or any other relevant connection or shared interest in connection with any Contract that may be entered into between the tenderer and WOAH as a result of the simplified consultation of suppliers;

It will inform, without delay, of any situation constituting a conflict of interest or which could give rise to a conflict of interest;

No offer of any type whatsoever from which an advantage can be derived under the Contract has been or will be made;

It has not granted and will not grant, has not sought and will not seek, has not attempted and will not attempt to obtain, and has not accepted and will not accept, any advantage, financial or in kind, to or from any party whatsoever, constituting an illegal practice or involving corruption, either directly or indirectly, as an incentive or reward relating to the award of the Contract;

It has not misrepresenting, either knowingly or negligently, in supplying any of the information requested by WOAH.

## Confidentiality

Unless otherwise authorised in writing by WOAH, all information, whether disclosed either directly or indirectly, formally or informally, in writing, orally, or by visual inspection, which are part of the tender procedure or provided for its purpose or any amendment thereto, shall not be disclosed, copied, used or modified in any manner and shall only be used for the sole purpose of the tender procedure.

Consequently, tenderers agree to take all the necessary steps to ensure compliance with such confidentiality obligations by its directors, officers and employees who need to know such information for purposes of the tender procedure. In addition, the tenderer undertakes to return to WOAH, upon first demand, any document transmitted, in line with the Confidentiality Undertaking signed.

All information received in response to this initiative that is marked proprietary will be handled accordingly. Responses will not be returned.

## Costs of Responses

Tenderers are responsible for all costs and expenses, including professional fees, incurred in connection with the preparation and submission of responses to, and generally their participation in, the tender procedure.

## Non-binding Effect

The information included in the tender documents are provided to Tenderers so they may prepare a proposal in response. This tender procedure may lead to the signature of a Contract between WOAH and a tenderer selected by WOAH. However, the transmission of the tender documents to tenderers does not imply any legal obligation on the part of WOAH to entrust the provision of the services to any tenderer. WOAH has the right to reject any proposal in its sole discretion. WOAH remains strictly independent of any tenderer, and none of the provisions of the tender documentation may be interpreted as creating a contractual relation of any sort.

WOAH is under no obligation to accept a given tenderer’s proposal and reserves the right not to proceed with, at any time prior to the signature of a Contract.

In this case, WOAH shall not have any liability whatsoever and tenderers who have not signed a Contract with WOAH waive their right to claim any compensation or damages.

## WOAH’s right

WOAH reserves itself the right to:

- qualify, accept or reject any or all tenderers as deemed to be the interest of WOAH,

- accept or reject any exception taken by the tenderers to the terms and conditions of the Specifications,

- cancel or modify the present tendering procedure,

- seek clarification from the tenderers about questions during the evaluation process,

- reject any tenderer who do not answer questions asked by WOAH during the evaluation process.

### Modification

WOAH reserves the right to introduce non-substantial modifications to the tender documents. In the event that WOAH, either following a request from a candidate / tenderer or on its own initiative, introduces a modification of the tender documents, all candidates / tenderers having downloaded the tender documents form, the WOAH contact point will be notified of such modification. WOAH may extend the deadline for submission of tenders to all candidates / tenderers to allow them to take into account these changes.

The fact that WOAH decides not to extend the deadline does not entitle candidate / tenderers to claim any compensation or to any form of complain whatsoever.

### Cancellation of the simplified consultation of suppliers

WOAH is not bound to follow up the tender.

WOAH also reserves the right to sign a Contract for only part of the Services. Such decisions would not entitle tenderers to any form of compensation whatsoever.

## Appeal

Tenderers believing that they have been harmed by an error or irregularity during the award process may lodge a complaint with WOAH by addressing their request to woah-procurement@woah.org or by letter to WOAH 12 rue de Prony 75017 Paris.

WOAH will be required to reply within ten working days after receipt of the complaint. If WOAH fails to address the complaint, the unsuccessful tenderer may request arbitration by the Permanent Court of Arbitration (PCA) at The Hague, governed by the PCA arbitration rules 2012 and the PCA Optional Rules for Arbitration between International Organisations and Private Parties.

# TENDER PROCESS DETAILS

## Procedure

The table below is an estimated schedule of the procedure. These dates are subject to be changed by WOAH depending on the length of the procedure.

All bidders will be informed should WOAH change any of these dates.

| Launching of the Simplified consultation of suppliers | 8/10/2026 |
| --- | --- |
| Deadline to receive bids | 6/11/2026 |
| Supplier selection | 15/11/2026 |

## Tender dossier

The tender documents are the following :

- Doc A - Tender procedure rules and its annex:

- WOAH contract template (Annex 1)

- Doc B - Administrative Information and its annexes:

- Declaration of integrity (Annex B1)

- Declaration of co-contracting (Annex B2)

- Declaration of subcontracting (Annex B3)

- Doc C - Financial Offer (to be filled and submitted as financial offer)

### Questions

During the simplified consultation of suppliers and up until WOAH starts discussions with one or several tenderers, the latter shall refrain from contacting the personnel of WOAH.

The Procurement Unit and the prescribing department, are the only representatives of the Organisation authorised to answer any questions.

Tenderers may wish to ask with the sole aim of obtaining additional technical, legal or administrative explanations, namely should they observe contradictions or omissions in the Specifications. They should send their questions to WOAH contact point. Questions may be asked up until 22nd  October 2026 at 06:00 p.m. (EAT).

To ensure fairness, any information given to one Candidate shall be immediately passed on to all the others. Likewise, during assessment of the applications and tenders, WOAH may request additional information from applications and tenders.

## Content of tenders and its selection

Tenders must be submitted in English and exclusively by electronic to the WOAH contact point.

Bidders shall send three files, as follows:

« First folder– Administrative Information »

« Second folder – Technical tender»

« Third folder – Financial tender »

These three files shall constitute the bid as follows :

- The first folder shall contain all the information and items requested in Administrative information document (Document B) and its annexes duly completed and signed:

- Declaration of integrity (Annex B1),

- Declaration of co-contracting (Annex B2) if any,

- Declaration of subcontracting (Annex B3) if any,

- The second file must contain the technical bid and any other information, other than that contained in the first and third file, which is part of the bid. No financial data shall be included in this bid. The file must also include

- WOAH contract template accepted in full” or present the modifications requested.

- The third folder must contain the financial tender (Document C) duly completed and signed.

Please make specific reference in the response to any legitimately and appropriately confidential or proprietary material contained in the response. Such information included in the responses to the simplified consultation of suppliers will be kept confidential by WOAH.

Reminder: responses should be submitted by 6 November 2026 6:00pm (EAT). 
Any proposal received past this deadline will be excluded from the simplified consultation of suppliers process.

To facilitate upload and management of your bid, you are invited:

To limit your bid at 70Mb,

Favor the following formats .doc / .rtf./ .pdf / .xls / zip. For the technical and financial bid, scanned documents will not be authorised and will not be analysed.

Avoid using other formats such as “.exe”

Avoid using certain tools such as “macros”

Check all files for viruses before sending them to the WOAH contact point

For each document that requires signature, signature shall emanate from a duly authorized person. This person is either the bidder’s legal representative or any person enjoying a delegation of powers or of signature emanating from the bidder’s legal representative.

## Proposal structure

Each tender must contain the following elements. If the tender does not contain all of these documents, WOAH reserves the right to exclude the tenderer.

### Information and Administrative documents

Bidder must complete and sign the following documents:

- Declaration of integrity (Annex B1),

- Declaration of co-contracting (Annex B2) if any,

- Declaration of subcontracting (Annex B3) if any,

### Technical response

- Management and implementation

The bid must provide information on the governance mechanism of the proposed project and a clear rationale for the organisation of the proposed activities. The main constraints and prerequisites (time, availability of parties involved) should be identified. A timetable with milestones should be provided.

The general project management methodology, including the scope and format of the supplier's monitoring, as well as measures to ensure that project deadlines are met, project costs are monitored and quality deliverables are delivered, will need to be identified.

- Team and profiles

Provide team profiles

- Risk factors

This section should provide a review of major constraints identified at this stage, potential risks to the project and requirements to ensure its successful completion. Prerequisites that you deem important to carry out the project effectively (time, stakeholder availability) should be identified.

Note: The technical offer should not be longer than 10 pages. Additional information relevant to the understanding of the response may be presented in annex and will not count against the maximum number of pages.

### Financial response

The financial offer should be provided in Euros, Document C and must be completed by each bidder. Only this appendix will be taken into account for the financial analysis of the bids.

- Financial offers should be provided in Euros and all applicable taxes and any other charges.

- Prices must be details as follows :

- Price excluding VAT,

- the amount of VAT if applicable,

- Price including VAT

- any other charges or duties must be detailed.

The prices indicated by the tenderer in the financial offer will be deemed to be inclusive of all costs, if any, as detailed below:

- the expenses required to provide the services specified

- any taxes and other possible charges applied on the services;

- any packaging, storage, wrapping, insurance and transport costs;

The tenders are invited to provide their estimated offer even if it exceeds the estimated budget.

#### Core Components

- The financial offer should provide on the document C with the following information:

- An overall cost;

- Cost breakdown

### Evaluation of tenders

WOAH will proceed to an evaluation of the provider according to the criteria described below:

Technical criteria (70%)

- Technical offer (40%)

- Experiences (30%)

- Team profile (30%)

Financial criteria (30%) will be assessed on the basis of the financial document C to be completed.

WOAH may ask tenderers to provide clarifications needed to evaluate their tender; tenderers will be requested to reply in writing.

## Regularisation of tenders

Any offer containing one or more substantial irregularities cannot be regularised and must therefore be rejected.

WOAH, at its sole discretion:

may ask tenderers/applicants having submitted an irregular offer (with no substantial irregularities) to regularise their offer within an appropriate period of time. If the tender is not regularised within the deadline, the tender/application will be rejected;

may decide not to regularise any irregular tenders/applications (with no substantial irregularities); in such case all irregular tenders/applications will be rejected.

In the event of a regularisation decision, WOAH may request any missing document or information, except for substantial ones (such as the Financial and Technical offers). If the tender is not regularised within the deadline, it will be rejected.

## Period of Proposal Validity

Tenderers are bound by their proposals for 180 days after the deadline for submission or until they have been notified of non-award. The successful tenderer must maintain its offer until the signature of the contract.

## Personal data

WOAH, as a data controller, will process the personal data you provide in the bidder for the purposes of identifying a suitable supplier, to support its work.

The data collected will be processed internally for the aforementioned purposes and for the resulting administrative acts, it shall be kept for the duration of the contract with you and in an intermediate archive for a duration of 10 during the audit period.

You have rights to access and rectify your personal data, as well as to request erasure and obtain data portability under certain circumstances.

To exercise these rights or If you have any questions about the processing of your data, you can contact our data protection officer at dpo@woah.org. For more information check our Privacy Policy: Privacy Policy - WOAH - World Organisation for Animal Health”.

## Publication of information on recipients

To comply with disclosure requirements and enhance transparency, WOAH shall publish on its website the following information about the Contract which shall be concluded with the awarded contractor: 
(i) the nature of the contract (ii) year of award (iii) name and locality of the Service provider; (iv) the title, purpose of the Service provider; and (v) the amount of this Agreement. WOAH will not release or publish information that could reasonably be considered confidential or proprietary.

## Awarding contract

WOAH will award the contract to the most technically and economically advantageous proposal, based on the above criteria (section 3.4.4.). Tenderers will be informed through electronic correspondence of the results of the selection process.

WOAH will submit to the selected bidder a service agreement.

If WOAH is unable to finalise a Contract with the Bidder ranked first, WOAH may proceed for the next ranked Bidder, and so on until a Contract is awarded.

# Annexes

Annex No. 1 – WOAH contract template